## Sheet1
Sl no | Tasks | Owner | Plan date | Remakrs
1 | Setup Zebi in Virtual Box | RK | 19/12/15
2 | Identify Storage Operations required for connctor | Saba | 19/12/15
3 | Develop Connector in Mistral | JP | 19/13/15 | Looking at the storage operations.. I feel that it would be better to go with Heat. Will see overall how we handle CRUD operation for objects based on inventory design, vSphere extension
4 | Develop Templates for Storage Operations | Mymoon | 19/14/15
5 | Develop Service Abstraction Connector for list calls | Asha | 19/12/15
6 | Develop vSphere extension for calling Templates | Vinod | 21/12/15
7 | Explore Abiquo UI and functionalities | Venky | 19/12/15
8 | Design UI required for Hyperconverged Orchestration | Venky | 20/12/15 | Refer Nimble Storage UI. Talk to Vinod.
9 | Talk to Hyper Converged Infra Consultant | Saba | 19/12/15
10 | Design Inventory functionality | Saba | 22/12/15 | Overall aspect on how we will handle inventory as a whole.